## Sheet1
S.No | Priority | Issue | Jira Ticket - Integration | Integration Sprint | Jira Ticket/Task- Fluent | Jira Ticket - ERP | Dpendency on BH | Clarification Required | Action owner | ETA | Comments | Status
1 | 1 | PO Invoice - mapping details/approach - how to send this to ERP? | BIN-165 | Sprint 13 | BFL-478 |  |  | Thomas will get back on this | Thomas | 30th Aug | 01/09- Mapping is done & now Prosenjit ( Monday) to Review Action - to check if CR exits in Fluent and Integration need to created new CR 04/09- No mapping is found. Refer the Link -> https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3219718145/Purchase+Order+Invoice+Registraion+-+ERP+BIN-165 20/09- Received updated JSON from ERP. Thomas needs to validate | Open | On hold until BHS approve the CR
2 |  | Credit Memo - mapping details/approach > How to send this to ERP - json from ERP and mapping from Fluent. | BIN-179 | Sprint 14 | BIN-477 | NA |  | Its a normal sales order but with negative lines, sync with Dobromir for details and Fluent team for web-hook details. | Prosenjit | 30th Aug |  | Open
3 | 1 | Sales Order lines updates - Fluent needs a provision to track the updates that have happened on So, so these can be shared with SF > Order revisions are planned for Sprint 13/14 a. Status at both the Order Level and Line Level for Order revisions b. Both Integration and Fluent needs to explore the possibilities of creating a diff between before and after - Prosenjit to check where BGh needs to use the diff. If the diff it not required in any system, then Salesforce can directly query fluent. | BIN-215 | Sprint 11 | BFL-471 |  | BIN-340 | Fluent needs to investigate how this can be done in fluent. Then we need to finalise the ChangedOrder Model with BGH. Related to 215 The before & After should be the entire sales order model and integration should try to do a diff between the 2. Mostly this will flow in Sprint 12. Anna will discuss this with Kim 30/8 | Anna T/Thomas | 30th Aug | 31/8- This discussion needs to happen with Kim and Martin Alm. 1/09 - Discussion still needs to take place. | Open | Needs to be assessed by Fluent (is it needed?)
4 |  | Stock Updates for SF - Fluent needs to send an event when products run out of stock > Need to create story in backlog. Thomas to share the relevant queries for fluent | BIN-143 | Sprint 12 | BIN-173 |  | BIN-17 | Agree on output model, product ref, qty, but also backInStock date, ..,.., Christoffer suggest output (check notes). https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3138846757/Stock+updates+-+feed#C)-Stock-position-API---as-required-from-eSales. Thomas will discuss with Martin Alm w.35 |  | 30th Aug | 31/08- Inputs provided by Thomas, Can be picked up by Integrations team. | Closed
5 | 1 | PO Header & Lines to ERP - Mapping required from Fluent – Expected by:18-Aug-2023 | BIN-67 | Sprint 12 | BIN-347 |  |  | ERP update is not working. Need mapping from fluent. Wait for BH to provide this |  | 30th Aug | Anna , pls add the open issues link here 31/8- Inputs provided by Thomas 1/09 - Thomas need discussion with Dobromir to finalize 19/09- Thomas need discussion with Deena to review the mapping 19/10 - Thomas needs to redesign. | Open | Charges will be skipped - can be built.
6 | 1 | PO Number Generation - Fluent story planned BFL-415 in sprint12 - mapping of pO number with PO | BIN-261 | Sprint 11 | BFL-415 |  |  | Fluent story done 30/8 |  | 30th Aug | 31/8- Inputs provided by Thomas | Closed
7 | 1 | Shipment delivery update events | BIN-157 | Sprint 13 | BFL-502 |  |  | Anna T/Thomas discuss with Kim | Anna T/Thomas | 30th Aug | 1/09 - discussion might take place on Wednesday | Open | Open OMS Topics - https://bygghemmagroup.sharepoint.com/:x:/r/sites/ProjectBob/_layouts/15/doc2.aspx?sourcedoc=%7B19d6b002-9913-4236-a691-7e4dd66804a3%7D&action=edit&activeCell=%27Sheet1%27!D10&wdinitialsession=df088591-8b68-443a-82cd-a79459ffad95&wdrldsc=8&wdrldc=1&wdrldr=AccessTokenExpiredWarning%2CRefreshingExpiredAccessT
8 |  | Fluent will have a manual retry system for initating freight booking - Findus to check with Kim | BIN-141 | Sprint 11 | Ticket to be created for Fluent |  |  | Anna T discuss with Kim | Anna T | 30th Aug | 1/09- got approval to proceed with the solution | Closed
9 |  | Freight Booking mapping for the error scenario | BIN-141 | Sprint 11 |  |  |  | Payload is updated. Thomas needs to revaluate and investigate | Thomas | 30th Aug | 31/8- Details provided 01/09 - Prosenjit to review 04/09- Reviewed. Can be closed | Closed
10 | 1 | Return Booking mapping | BIN-204,BIN-292,BIN-358 | Sprint 13 | BFL-457 |  |  | Clarification Required from BH - Hilde will book a meeting for w.37 | Thomas/Prosenjit | 30th Aug | 1/09 - Need to discuss this with BH (Rubin & kim) for clarification - Hilde is planning meeting for the same | Open | Waiting for BHS to clarify
11 | 1 | Dispatch advice entity ID vs entity ref | [5 empty] | Thomas will get back on this | Thomas | 30th aug | This is an open topic which fluent has to verifiy for entire design. 1/09- Details have been provided Action - Mateen Needs to review from Development persective | Closed
12 | 1 | Post Sales Invoice Integration | BIN-211 | Sprint 13 | BFL-479 |  |  | ERP to share the sales invoice details |  |  | This will be a new approach to handle PO invoices both in fluent and ERP 1/09 - Fluent Needs to provide the mapping | Open
13 |  | Purchase order / invoice interfacing changes with ERP [NEW Approach] | TBD | [8 empty] | Open
14 |  | Replenishment PO Creation [ Planned PO] | BIN-135, BIN-136 | Sprint 14 | BFL-503 | [5 empty] | https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3231219740/Planned+Purchase+Order | Open
15 |  | Customer Notification events Integration | BIN-104 | Sprint 14 | BFL-504 | [5 empty] | https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3128558265/Customer+Notification+Notification+events+Integration+-+BIN-104 | Open
16 |  | New Payment by invoice | BIN-116 |  | BFL-515 |  |  | Fluent to share webhook , query, Data Model
17 |  | New payment by link | BIN-114 |  | BFL-516 |  |  | Fluent to share webhook , query, Data Model
18 |  | New Payment status update in Fluent | BIN-115 |  | BFL-520 |  |  | Fluent to share webhook , query, Data Model
19 |  | Payment Capture status update in Fluent | BIN-110 |  | BFL-521 |  |  | Fluent to share webhook , query, Data Model
20 |  | Payment capture | BIN-107 |  | BFL-522 |  |  | Fluent to share webhook , query, Data Model
21 |  | Payment refund | BIN-186 |  | BFL-523 |  |  | Fluent to share webhook , query, Data Model
22 |  | Payment Refund status update in fluent | BIN-212 |  | BFL-524 |  |  | Fluent to share webhook , query, Data Model
23 |  | Payment update amount Integration | BIN-188 |  | BFL-525 |  |  | Fluent to share webhook , query, Data Model
24 |  | Payment update amount status update in Flueent | BIN-213 |  | BFL-526 |  |  | Fluent to share webhook , query, Data Model
25 |  | Payment verification from Payment gateway | BIN-109 |  | BFL-527 |  |  | Fluent to share webhook , query, Data Model
26 |  | Cancel Payment | BIN-210 |  | BFL-528 |  |  | Fluent to share webhook , query, Data Model
27 |  | Transformation of Bank File - ERP | BIN-208 |  | Ticket to be created
28 |  | Cancel Payment status update in Fluent | BIN-214 |  | BFL-529 |  |  | Fluent to share webhook , query, Data Model
29 |  | Fraud Service | BIN-194 |  | BFL-530 |  |  | Fluent to share webhook , query, Data Model
30 |  | Catalogue refs at the time of product creation is - BH:PC:MASTER and now when querying virtual stock position is different as on this page = https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3247374337/Virtual+Stock+position+API+Event+-+Integration+eSales+P2E+BIN-143 | BIN-143 | [8 empty] | closed
31 |  | Error Responses structure -Fluent . |  |  | BFL-531 | [5 empty] | 12/09- Fluent needs to review and implement the standardize way of returning error response. Refer email reference of 12/09 | Open
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
|  | Catalogue refs at the time of product creation is - BH:PC:MASTER and now when querying virtual stock position is different as on this page = https://bygghemma-it.atlassian.net/wiki/spaces/BDT/pages/3247374337/Virtual+Stock+position+API+Event+-+Integration+eSales+P2E+BIN-143 | BIN-143 | [8 empty] | Open

## Sheet4
Base Scope | Changes | CRs
|  | Open topics list to be discussed with Kim | Prioritised