## README - Report Guide
Sprint Delivery Report — Report Guide
Read this before using the Master/Pivot tabs. Last reviewed: Aug 2026 (delivery-exec pass).
1. What this workbook contains
Master sheets | One row per Application/Area. Sprint-level values for Productivity, Velocity, Predictability, Defect Density, and Defects. Same Domain/Workstream/App/Active-App columns are repeated across all five — keep them in sync manually (see Data Quality Flags tab for known drift).
Pivot sheets | Roll-ups by Workstream, one per metric. Converted to static values during this review (see note 5 below) — refresh manually against the Master sheets if source data changes.
Review4 / Review5 | Portfolio-level monthly trend (Oct'25–Jun'26). Two different 'Productivity' figures exist for the same months — see Data Quality Flags tab, item DQ-06, before quoting these numbers.
Productivity Insights / Lead Observations | Narrative summary and per-application owner questions, built off the Pivot Productivity data.
2. Key metric definitions
Productivity | Velocity ÷ number of contributing FTEs for the period ('SP per member').
Velocity | Total story points accepted in a sprint/period.
Predictability | SP accepted ÷ SP planned for a sprint. Should sit close to 1.0 (100%) if planning is reliable; values far above 1.5x or below 0.5x usually indicate the plan or accept number is being entered inconsistently rather than genuine over/under-delivery.
PRD Defect Density % | Post-production defects (within 23 days of release) ÷ story points delivered.
Q3TD | 'Q3 to date' — a partial quarter (as few as 3 of ~7 sprints). Treat as directional only.
3. Known limitations (read before presenting this externally)
Partial periods look identical to complete ones | Q3TD averages and Jun'26 in Review4/5 use the same formatting as fully-populated quarters/months. A 'Period Coverage' / 'Coverage Flag' column has been added to Master Productivity and Review4/Review5 in this revision to make this visible at a glance.
Active App flag is not reliable | Two apps are marked Active = No while still carrying live headcount and delivery data (Einstein 360, XM360 Recovery/Reliability). Flagged in yellow on Master Productivity and logged in Data Quality Flags.
Untraceable rows | Master Productivity rows without an SL No / App name but containing sprint values have been highlighted in red with a Data Quality Note. Do not include these in any total until attributed.
Defect logging gaps | The entire Payment & Billing workstream shows 0.000000% defect density across 12 consecutive sprints — more likely an untracked/unlogged metric than a genuine zero-defect result.
4. Recommended next steps for the report owner
1. | Decide, and document, one authoritative formula for portfolio 'Productivity' (Review4 column B vs column F disagree by ~8%).
2. | Standardize the Review4/Review5 divisor logic and document any exception with a stated reason.
3. | Attribute or delete the unattributed data rows in Master Productivity (highlighted red).
4. | Reconcile the Active App flag for Einstein 360 and XM360 Recovery/Reliability with actual staffing.
5. | Confirm whether defect logging is actually wired up for the Payment & Billing workstream.
6. | Consolidate the five Master sheets onto shared App/Workstream reference data (e.g. via lookup formulas) instead of five independently-maintained copies, to stop the Active-App and naming drift seen above.
5. What changed in this revision
• | Added this README and the 'Data Quality Flags' tab (consolidated issue log).
• | Master Productivity: added 'Sprints Reported', 'Coverage Flag', and 'Data Quality Note' columns; highlighted 7 unattributed data rows (red) and 2 Active-App inconsistencies (yellow).
• | Review4: labeled the previously-unnamed helper column F and flagged its mismatch with column B; added 'Period Coverage'.
• | Review5: added 'Period Coverage', flagging Jun'26 (partial) and Dec'25 (non-standard divisor).
• | Pivot tables were converted to static values by the recalculation engine used for this review — they no longer auto-refresh from a pivot cache. Rebuild them as live pivots in Excel if that functionality is still needed.

## Data Quality Flags
Data Quality Flags — Consolidated Issue Log
Every row is a specific, verifiable issue found while reviewing this workbook. Resolve or annotate before recirculating.
ID | Sheet(s) | Location | Severity | Issue | Evidence | Recommended action
DQ-01 | Master Productivity | Rows 31-35, 37, 38 (cols L, V) | High | Untraceable sprint data | 7 rows contain live values (Sp17 and Sp1 productivity figures, e.g. 5, 10, 14, 9.07, 8, 6.4) with no SL No, Domain, Workstream, or Application/Area attached. | Attribute to the correct application or delete before this report is recirculated. Do not include in any total until resolved.
DQ-02 | Master Productivity / Master Data Velocity | Row 10 (XM360 Recovery/Reliability), Row 22 (Einstein 360) | High | Active App = 'No' but app is fully staffed and delivering | XM360 Recovery/Reliability shows 6.5 Developer/QA in Q3/Q4 with ongoing sprint velocity; Einstein 360 shows 4.0 FTE with continuous Sp16-26 delivery data. Both flagged 'Active App: No'. | Confirm with the app owners whether the Active flag or the delivery data is stale, and correct one of them.
DQ-03 | Master Data Predictability | Flow Engine (optimus) row; CPOS row | High | Predictability ratio is not a believable signal | Flow Engine (optimus), a 2-person team, shows sprint predictability of 12.0x, 5.67x (x3), 5.33x, 4.43x, 4.4x, 3.57x, 3.33x, 3.25x, 2.16x, 2.0x planned capacity. CPOS swings between 0.28x and 4.67x. | Audit how 'SP planned' is captured for these two teams — a metric this volatile is more likely a data-entry issue than genuine delivery variance.
DQ-04 | Master Defects | XM360 CBM/Phoenix, Sp 6 column | Medium | Defect count outlier | 81 defects logged in Sp6 vs 5, 7, 9, 24, 28 in the surrounding sprints for the same app — roughly 3x the next-highest sprint for this app. | Verify this is a real quality incident (and capture root cause) rather than a data entry error, since it did not move PRD Defect Density that sprint.
DQ-05 | Pivot PRD Defect Density | Payment & Billing rows, Q1 and Q2 columns | Medium | Suspiciously clean defect data | All four Payment & Billing scrums (XRM - VOIXM/Video/HSD, DevOps) report exactly 0.000000% defect density across 12 consecutive sprints. | Confirm defects are actually being logged against this workstream's apps, rather than tracked in a separate system that doesn't feed this report.
DQ-06 | Review4 | Column B vs Column F | High | Two disagreeing 'Productivity' figures for the same months | Column B is a hardcoded value (no formula). Column F (labeled here for the first time) is a live formula '=Velocity/FTE contributing/divisor'. For Oct'25 they read 7.22 vs 6.67 — an 8% gap — and every other month disagrees similarly. | Pick one authoritative definition and make column B a live formula referencing it, so the two can never drift again.
DQ-07 | Review4 / Review5 | Row 10 (Jun'26) | Medium | Partial month presented like a complete one | Jun'26 uses a productivity divisor of 1 vs 2 for every other month, because it is a half-reported period. Velocity (868) looks like a cliff next to May'26 (1,785) purely because of this. | Label partial months explicitly wherever this trend is charted (now done via the new 'Period Coverage' column) so viewers don't read it as a real decline.
DQ-08 | Review5 | Row 4 (Dec'25) | Low | Undocumented divisor exception | Dec'25 uses a productivity divisor of 3, the only month that isn't 1 or 2, with no note explaining why. | Add a one-line reason (e.g. extra pay period / 3-sprint month) so the exception doesn't look like an error.
DQ-09 | Master Productivity | App-level, e.g. CPOS | Medium | Quarterly averages built from very sparse sprint data | CPOS has real values in only 3 of 15 tracked sprints (Sp12-26), yet its quarterly averages are displayed with the same formatting/confidence as fully-populated apps. | Use the new 'Sprints Reported' / 'Coverage Flag' columns added to this sheet to caveat any app below ~50% coverage in commentary.
DQ-10 | All five Master sheets | Domain/Workstream/App/Active-App columns | Medium | Same reference data duplicated across 5 sheets | Productivity, Velocity, Predictability, Defect Density, and Defects each maintain their own copy of Domain/Workstream/Application/Active-App. DQ-02 shows these have already drifted. | Long-term: maintain one reference table (App × Domain × Workstream × Active flag) and have each Master sheet look it up, instead of five independently hand-maintained copies.

## Master Productivity
SL No | Domain | Workstream | QBR | Application/Area | Active App | Sp 12 Scrum Productivity in SP (Velocity by member) | Sp 13 Scrum Productivity in SP (Velocity by member) | Sp 14 Scrum Productivity in SP (Velocity by member) | Sp 15 Scrum Productivity in SP (Velocity by member) | Sp 16 Scrum Productivity in SP (Velocity by member) | Sp 17 Scrum Productivity in SP (Velocity by member) | Sp 18 Scrum Productivity in SP (Velocity by member) | Sp 19 Scrum Productivity in SP (Velocity by member) | Sp 20 Scrum Productivity in SP (Velocity by member) | Sp 21 Scrum Productivity in SP (Velocity by member) | Sp 22 Scrum Productivity in SP (Velocity by member) | Sp 23 Scrum Productivity in SP (Velocity by member) | Sp 24 Scrum Productivity in SP (Velocity by member) | Sp 25 Scrum Productivity in SP (Velocity by member) | Sp 26 Scrum Productivity in SP (Velocity by member) | Avg of 15 SP (From 12 to 26) | Avg Of Q3 Sprints(SP 14 to 19) | Avg Of Q4 Sprints(SP 20 to 26) | Sp 1 Scrum Productivity in SP (Velocity by member) | Sp 2 Scrum Productivity in SP (Velocity by member) | Sp 3 Scrum Productivity in SP (Velocity by member) | Sp 4 Scrum Productivity in SP (Velocity by member) | Sp 5 Scrum Productivity in SP (Velocity by member) | Sp 6 Scrum Productivity in SP (Velocity by member) | Avg Of Q1 Sprints(SP 1 to 6) | Sp 7 Scrum Productivity in SP (Velocity by member) | Sp 8 Scrum Productivity in SP (Velocity by member) | Sp 9 Scrum Productivity in SP (Velocity by member) | Sp 10 Scrum Productivity in SP (Velocity by member) | Sp 11 Scrum Productivity in SP (Velocity by member) | Sp 12 Scrum Productivity in SP (Velocity by member) | Avg Of Q2 Sprints(SP 7 to 12) | Sp 13 Scrum Productivity in SP (Velocity by member) | Sp 14 Scrum Productivity in SP (Velocity by member) | Sp 15 Scrum Productivity in SP (Velocity by member) | Sp 16 Scrum Productivity in SP (Velocity by member) | Sp 17 Scrum Productivity in SP (Velocity by member) | Sp 18 Scrum Productivity in SP (Velocity by member) | Sp 19 Scrum Productivity in SP (Velocity by member) | Avg Of Q3 Sprints(SP 13 to 15) | Sprints Reported (Sp12-26, of 15) | Coverage Flag | Data Quality Note
1 | IXT | CEUI | Assisted Tools | CPOS | Yes | [12 empty] | 4.6667 | 3.6667 | 6.5 | 4.9444 |  | 4.9444 | 3.25 | 6.75 | 8.25 | 5.5 | 3 | 10.5 | 6.2083 | 7.25 | 5.75 | 5.6 | 5.2 | 6.75 | 8 | 6.425 | 8 | 7.25 | 0 |  |  |  |  | 5.0833 | 3 | Low coverage
2 | IXT | CEUI | Assisted Tools | Xumo | Yes | 9.5714 | 10.5714 | 12 | 8.8 | 8.9091 | 9.8182 | 9 | 9.3333 | 9.0769 | 8.1538 | 8 | 10.3077 | 10.62 | 8.46 | 3.7 | 9.0881 | 9.6434 | 8.3312 | 7.82 | 7.27 | 9.2 | 10.4 | 9.8 | 9.4 | 8.9817 | 10 | 10.6 | 10.6 | 10.4 | 10.6 | 11.8 | 10.6667 | 10.8 | 13.8 | 10.2 |  |  |  |  | 11.6 | 15 | Full
3 | IXT | CEUI | Platform | Flow Engine (prometheus) | Yes | 3.1111 | 3.5556 | 2.2222 | 2.8889 | 3.3333 | 3 | 2.4 | 4.3 | 3.9 | 5 | 4 | 3.5556 | 4.06 | 3.94 | 5.1111 | 3.6252 | 3.0241 | 4.2238 | 3 | 4.33 | 4 | 4.33 | 4.22 | 3.56 | 3.9067 | 4.1111 | 3.7778 | 4.11 | 4.8889 | 5.33 | 5.3889 | 4.6011 | 5 | 5.56 | 5.6667 |  |  |  |  | 5.4089 | 15 | Full
4 | IXT | CEUI | Platform | Flow Engine (optimus) | Yes | 4.25 | 4 | 5.25 | 5 | 4.25 | 4 | 3.25 | 4.75 | 4.3 | 4 | 3.5 | 5 | 4.5 | 4.25 | 4 | 4.2867 | 4.4167 | 4.2214 | 3.25 | 4.25 | 4.75 | 5 | 6 | 3.25 | 4.4167 | 4.25 | 4 | 4.5 | 5 | 4 | 4 | 4.2917 | 3.25 | 5 | 5.25 |  |  |  |  | 4.5 | 15 | Full
5 | IXT | CEUI | Platform | Celestial (Titan) | Yes | 7.8333 | 7.1667 | 10 | 12.5 | 13.3333 | 7.8333 | 13.6667 | 11.1667 | 11.2 | 11.4 | 10.8 | 10 | 12 | 11 | 7.2 | 10.4733 | 11.4167 | 10.5143 | 11.4 | 13 | 12.6 | 12 | 12.4 | 9.5714 | 11.8286 | 12.8 | 14.2 | 13.2 | 14 | 12 | 12 | 13.0333 | 13.2 | 14 | 15 |  |  |  |  | 14.0667 | 15 | Full
6 | IXT | CEUI | Platform | Celestial (Universal) | Yes | 7.6364 | 6.9091 | 7.3333 | 8.5 | 8.1667 | 8 | 5.8333 | 8.3333 | 8.2857 | 7.9 | 8.2857 | 7.1429 | 7.43 | 7.57 | 9.3 | 7.7751 | 7.6944 | 7.9878 | 9 | 8.28 | 9.14 | 9.71 | 8.86 | 8.25 | 8.8733 | 9 | 9.2857 | 9.14 | 9.5714 | 10.14 | 9.5714 | 9.4514 | 10.57 | 9.86 | 10.1429 |  |  |  |  | 10.191 | 15 | Full
7 | IXT | CEUI | Platform | Right Answers | Yes | 8.5 | 9 | 7.5 | 8.5 | 9 | 9 | 8.5 | 13 | 9 | 7.5 | 6.5 | 3.5 | 6.5 | 4 | 6 | 7.7333 | 9.25 | 6.1429 | 3 | 4.5 | 2 | 2 | 7.33 | 6.6667 | 4.2494 | 11.5 | 12.5 | 5.5 | 10.5 | 9.5 | 10.5 | 10 | 11 | 9 | 10 |  |  |  |  | 10 | 15 | Full
8 | IXT | CEUI | Assisted Tools | XM360 CBM/Phoenix | Yes | 4.5 | 5 | 3 | 9 | 3.4286 | 7.8571 | 5 | 8.1429 | 8.375 | 8.25 | 7.875 | 9.75 | 7.5 | 4.87 | 5.125 | 6.5116 | 6.0714 | 7.3921 | 3.75 | 7.25 | 8.5 | 10.12 | 7.38 | 7.625 | 7.4375 | 7.25 | 5.125 | 6.38 | 5.125 | 4.88 | 6.125 | 5.8142 | 5.13 | 5.88 | 4.875 |  |  |  |  | 5.295 | 15 | Full
9 | IXT | CEUI | Assisted Tools | XM360 Recovery/Reliability | No | 7.8571 | 7.1429 | 6.375 | 5.375 | 5.625 | 5.5 | 4.3077 | 5.8462 | 6.9231 | 8 | 9.0769 | 8.4615 | 7.85 | 7.69 | 6.9231 | 6.8636 | 5.5048 | 7.8464 | [22 empty] | 15 | Full | Active App = No, but this app carries live headcount and delivery data elsewhere in the workbook (see Data Quality Flags tab). Confirm whether the Active App flag or the delivery data is correct.
10 | IXT | CEUI | Assisted Tools | XM360 Supersonix | Yes | 3.6 | 5.2 | 7.7333 | 5.7333 | 6 | 6.2667 | 6.2222 | 4.8889 | 6.2222 | 7.1111 | 8.6667 | 10.4444 | 7.33 | 6 | 6.4444 | 6.5242 | 6.1407 | 7.4598 | 3.38 | 7.75 | 8.25 | 7.12 | 9.88 | 9.375 | 7.6258 | 7.375 | 8.25 | 8.75 | 9.375 | 6.38 | 4.75 | 7.48 | 5.25 | 5.38 | 5.5 |  |  |  |  | 5.3767 | 15 | Full
11 | IXT | CEUI | Assisted Tools | XM Velocity 1/Xceeders | Yes | 1.6923 | 6.3077 | 3.0769 | 2.4615 | 6.4615 | 3.3846 | 4.4615 | 5.5385 | 7.0769 | 6.3077 | 3.0769 | 7.0769 | 5.69 | 6.5 | 4 | 4.8742 | 4.2308 | 5.6755 | 6.92 | 7.5 | 6.29 | 7.85 | 6.31 | 7.2308 | 7.0168 | 5.8462 | 5.8462 | 5.69 | 9.08 | 8.17 | 9 | 7.2721 | 5.82 | 9 | 8.73 |  |  |  |  | 7.85 | 15 | Full
12 | IXT | CEUI | Assisted Tools | XM Velocity 2/Xplorers | Yes | 3.6923 | 10.3077 | 5.3333 | 1.8667 | 3.3333 | 3.3333 | 4.2667 | 4.6667 | 5.2 | 2.8 | 3.8667 | 5.0667 | 4.26 | 4.5 | 3.8667 | 4.424 | 3.8 | 4.2229 | 6.13 | 4.9 | 6 | 7.83 | 4.33 | 7.8333 | 6.1706 | 6.8333 | 6.0833 | 4.46 | 7.8462 | 7.8571 | 6.5714 | 6.6086 | [8 empty] | 15 | Full
13 | IXT | Field experience | Field Experience | NWT - UI | Yes | 9.5349 | 6.7442 | 8.1176 | 7.8 | 8.9 | 8.3 | 8.2 | 10.8 | 5.9 | 9.1 | 6.6 | 7.4117 | 8 | 6.9 | 6.3529 | 7.9108 | 8.6863 | 7.1807 | 7.41 | 5.1 | 11.1 | 9.7 | 7.29 | 6 | 7.7667 | 7.8 | 9.6 | 7.4 | 13.4 | 5 | 7.3333 | 8.4222 | 5.83 | 8.5 | 10 |  |  |  |  | 8.11 | 15 | Full
14 | IXT | Field experience | Field Experience | NWT-FSM | Yes |  |  |  | 6.6 | 4.9 | 5.7 | 4 | 5.7 | 7.7 | 5.7 | 2.9 | 4.5714 | 6 | 3.3 | 8 | 5.4226 | 5.38 | 5.4531 | 2 | 5.3 | 5.3 | 7 | 6.29 | 4.8571 | 5.1245 | 9.2 | 8.4 | 5.33 | 8 | 6.8 | 10.8 | 8.0883 | 10 | 8.7 | 8.4 |  |  |  |  | 9.0333 | 12 | Partial
15 | IXT | Field experience | Field Experience | NWT - PSNB | Yes | 9.4444 | 11.9444 | 7.75 | 9.5 | 8.5 | 8.25 | 7 | 9.5 | 7 | 10.75 | 7.8 | 9 | 13.65 | 9 | 3.75 | 8.8559 | 8.4167 | 8.7071 | 10 | 7 | 8.8 | 5.8 | 8.25 | 4.5 | 7.3917 | 8.5 | 6 | 5.5 | 4.5 | 5.5 | 5.25 | 5.875 | 5.5 | [6 empty] | 5.5 | 15 | Full
16 | IXT | Field experience | Field Experience | NWT - Core | Yes | 9.3 | 8.8 | 8.5 | 9.1 | 9.2 | 7.9 | 7.8 | 8.8 | 6.2 | 7.2 | 9.1 | 8.8 | 9 | 8.9 | 7.6 | 8.4133 | 8.55 | 8.1143 | 6.6 | 7.9 | 8.8 | 8.8 | 8.2 |  | 8.06 | 0.89 | 6.2 | 5.8 | - |  |  | 4.2967 | [8 empty] | 15 | Full
17 | IXT | Payment & Billing | XRM | XRM - VOIXM Scrum | Yes | 5.3333 | 4 | 2.6364 | 3.8182 | 4.7273 | 5.1818 | 3.9 | 5 | 5.2 | 5.5 | 5.4 | 5.2 | 5.9 | 5.9 | 5.4 | 4.8731 | 4.2106 | 5.5 | 4.9 | 5.6 | 5.36 | 6.81 | 6 | 6.5455 | 5.8692 | 6.4 | 6.7 | 5.8 | 5.9 | 5.2 | 5.2 | 5.8667 | 5.3 | 6 | 5.4 |  |  |  |  | 5.5667 | 15 | Full
18 | IXT | Payment & Billing | XRM | XRM - Video Scrum | Yes | 4.9 | 7.3 | 6.2727 | 6.9091 | 7.5455 | 6.3636 | 5.7273 | 6.7273 | 6 | 6.9 | 6.5 | 6.4 | 6.1 | 6.1 | 4.7273 | 6.2982 | 6.5909 | 6.1039 | 5.9 | 5.6 | 7.45 | 7.18 | 6.45 | 5.9091 | 6.4148 | 6.8 | 6.1 | 5.27 | 6.2727 | 7.0909 | 6.8182 | 6.392 | 7.09 | 7 | 7.0909 |  |  |  |  | 7.0603 | 15 | Full
19 | IXT | Payment & Billing | XRM | XRM - HSD Scrum | Yes | 4.4444 | 5.4444 | 4.6 | 4.9 | 4.7 | 5.3 | 5.5 | 5.4 | 4.3 | 6.3 | 5.9 | 4.5 | 2.2 | 5 | 3.43 | 4.7946 | 5.0667 | 4.5186 | 3 | 4.5 | 4.82 | 5.36 | 6.58 | 5.0833 | 4.8906 | 5.3636 | 5.2818 | 5.7 | 5.2 | 4.5 | 8 | 5.6742 | 3.6 | 4.8 | 5.5 |  |  |  |  | 4.6333 | 15 | Full
20 | IXT | Payment & Billing | BXT | DevOps | Yes | 7.1 | 5.4 | 6.2222 | 6.3333 | 5.4444 | 4.6667 | 6.7778 | 6.1111 | 6.1111 | 3.5556 | 5.11 | 6 | 5.77 | 3.88 | 3.3333 | 5.4544 | 5.9259 | 4.8229 | 6.22 | 6.11 | 6.11 | 6.33 | 6.44 | 6.5 | 6.285 | 5.4444 | 6.6667 | 6.22 | 7 | 7.22 | 8.2222 | 6.7956 | 9.56 | 8.78 | [5 empty] | 9.17 | 15 | Full
21 | IXT | CEUI | Assisted Tools | Einstein 360 | No |  |  |  |  | 1.25 | 8 | 5.5 | 5.5 | 8 | 5.5 | 5.75 | 5.25 | 6.75 | 3.25 | 5.5 | 5.4773 | 5.0625 | 5.7143 | [22 empty] | 11 | Partial | Active App = No, but this app carries live headcount and delivery data elsewhere in the workbook (see Data Quality Flags tab). Confirm whether the Active App flag or the delivery data is correct.
22 | IXT | Payment & Billing | Account Services | Account Services - BRE | Yes | [8 empty] | 16 | 13 | 13 | 14.5 | 9 | 7.5 | 12 | 12.1429 | 12.1429 | 12.1429 | 12 | 11.5 | 14 | 11.5 | 12 | 9 | 11.6667 | 13 | 14 | 14 | 15 | 12.5 | 13.5 | 13.6667 | 10.5 | 12 | 12 |  |  |  |  | 11.5 | 7 | Partial
23 | IXT | Payment & Billing | Account Services | Account Services - XM PDF | Yes | [8 empty] | 10 | 8.25 | 12.75 | 12.75 | 10.25 | 6 | 2.25 | 8.8929 | 8.8929 | 8.8929 | 14 | 14 | 12.67 | 11.33 | 8.75 | 9.6667 | 11.7361 | 6 | 12 | 11.75 | 11.5 | 10 | 9.8 | 10.175 | 8.6 | 10 | 9.2 |  |  |  |  | 9.2667 | 7 | Partial
24 | IXT | Payment & Billing | Account Services | Account Services - NOW | Yes | [8 empty] | 5 | 6.5 | 8 | 11.5 | 2.5 | 1 | 2.5 | 5.2857 | 5.2857 | 5.2857 |  |  |  |  | 8.5 | 6.5 | 7.5 | 10 | [5 empty] | 10 | [8 empty] | 7 | Partial
25 | IXT | Agile Portfolio Mgmt |  | Scrum Master | [41 empty] | 0 | Low coverage
26 | IXT | Payment & Billing |  | Scrum Master | [41 empty] | 0 | Low coverage
27 | IXT | Payment & Billing |  | DBA Scrum | [41 empty] | 0 | Low coverage
28 | IXT | Field experience | Field Experience | NWT-FSM 2 (NOVA) | Yes | [25 empty] | 3.3333 | 9 | 4 | 8.5 | 7.5 | 3.5 | 5.9722 | 7 | [6 empty] | 7 | 0 | Low coverage
[15 empty] | 5 | [5 empty] | 14 | [26 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 5 | [5 empty] | 10 | [26 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 10 | [5 empty] | 10 | [26 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 10 | [5 empty] | 11.3333 | [26 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 10 | [5 empty] | 9.0667 | [26 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 8 | [32 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.
[15 empty] | 6.4 | [32 empty] | ⚠ UNATTRIBUTED DATA — values exist in this row (see original Sp columns) with no SL No, Domain, Workstream, or Application name. Cannot be attributed to any app/owner. See Data Quality Flags tab.

## Pivot Productivity
Workstream | - all - |  |  |  |  | 26Q2 Vs 26Q1
Active App | Yes |  |  |  |  | 26Q2 Vs 25Q4
Row Labels | Q3 (SP 14 to 19) | Q4 (SP 20 to 26) | Q1 (SP 1 to 6) | Q2 (SP 7 to 12) | Q3 (SP 13 to 15)
Account Services | 8.7738 | 8.7738 | 10.3009 | 11.2806 | 10.3833
Account Services - BRE | 12.1429 | 12.1429 | 11.6667 | 13.6667 | 11.5
Account Services - NOW | 5.2857 | 5.2857 | 7.5 | 10
Account Services - XM PDF | 8.8929 | 8.8929 | 11.7361 | 10.175 | 9.2667
Assisted Tools | 5.9773 | 6.3377 | 7.2401 | 7.3777 | 7.041
CPOS |  | 4.9444 | 6.2083 | 6.425 | 5.0833
XM Velocity 1/Xceeders | 4.2308 | 5.6755 | 7.0168 | 7.2721 | 7.85
XM Velocity 2/Xplorers | 3.8 | 4.2229 | 6.1706 | 6.6086
XM360 CBM/Phoenix | 6.0714 | 7.3921 | 7.4375 | 5.8142 | 5.295
XM360 Supersonix | 6.1407 | 7.4598 | 7.6258 | 7.48 | 5.3767
Xumo | 9.6434 | 8.3312 | 8.9817 | 10.6667 | 11.6
BXT | 5.9259 | 4.8229 | 6.285 | 6.7956 | 9.17
DevOps | 5.9259 | 4.8229 | 6.285 | 6.7956 | 9.17
Field Experience | 7.7582 | 7.3638 | 7.0857 | 6.5309 | 7.4108
NWT - Core | 8.55 | 8.1143 | 8.06 | 4.2967
NWT - PSNB | 8.4167 | 8.7071 | 7.3917 | 5.875 | 5.5
NWT - UI | 8.6863 | 7.1807 | 7.7667 | 8.4222 | 8.11
NWT-FSM | 5.38 | 5.4531 | 5.1245 | 8.0883 | 9.0333
NWT-FSM 2 (NOVA) |  |  |  | 5.9722 | 7
Platform | 7.1604 | 6.618 | 6.6549 | 8.2755 | 8.8333
Celestial (Titan) | 11.4167 | 10.5143 | 11.8286 | 13.0333 | 14.0667
Celestial (Universal) | 7.6944 | 7.9878 | 8.8733 | 9.4514 | 10.191
Flow Engine (optimus) | 4.4167 | 4.2214 | 4.4167 | 4.2917 | 4.5
Flow Engine (prometheus) | 3.0241 | 4.2238 | 3.9067 | 4.6011 | 5.4089
Right Answers | 9.25 | 6.1429 | 4.2494 | 10 | 10
XRM | 5.2894 | 5.3742 | 5.7249 | 5.9776 | 5.7534
XRM - HSD Scrum | 5.0667 | 4.5186 | 4.8906 | 5.6742 | 4.6333
XRM - Video Scrum | 6.5909 | 6.1039 | 6.4148 | 6.392 | 7.0603
XRM - VOIXM Scrum | 4.2106 | 5.5 | 5.8692 | 5.8667 | 5.5667
Total Result | 6.897 | 6.7199 | 7.2464 | 7.6899 | 7.8106

## Master Data Velocity
Domain | Workstream | QBR | Application/Area | Active App | Story Points accepted in Sp 12 | Story Points accepted in Sp 13 to date | Story Points accepted in Sp 14 | Story Points accepted in Sp 15 to date | Developer/QA Count | Story Points accepted in Sp 16 | Story Points accepted in Sp 17 to date | Developer/QA Count | Story Points accepted in Sp 18 | Story Points accepted in Sp 19 to date | Developer/QA Count | Developer/QA Count in Q3 (SP 14 to 19) | Total Story points Delivered across sprints in Q3(SP 14 to 19) | # of Sprints in Q3 (SP 14 to 19) | Avg USP / SP in Q3 (SP 14 to 19) | Avg USP / Month In Q3(SP 14 to 19) | Story Points accepted in Sp 20 | Story Points accepted in Sp 21 | Developer/QA Count | Story Points accepted in Sp 22 | Story Points accepted in Sp 23 | Story Points accepted in Sp 24 | Story Points accepted in Sp 25 | Story Points accepted in Sp 26 | Developer/QA Count in Q4 (SP 20 to 26) | Total Story points Delivered across sprints in Q4(SP 20 to 26) | # of Sprints in Q4 (SP 20 to 26) | Avg USP / SP in Q4 (SP 20 to 26) | Avg USP / Month In Q4(SP 20 to 26) | Developer/QA Count | Total Story points Delivered across sprints | # of Sprints | Avg USP / SP | Avg USP / Month | Story Points accepted in Sp 1 | Story Points accepted in Sp 2 to date | Story Points accepted in Sp 3 | Story Points accepted in Sp 4 to date | Story Points accepted in Sp 5 | Story Points accepted in Sp 6 | Developer/QA Count in Q1 | Total Story points Delivered across sprints in Q1 | # of Sprints in Q1 | Avg USP / SP in Q1 (SP 1 to 6) | Avg USP / Month In Q1 (SP 1 to 6) | Story Points accepted in 7 to date | Story Points accepted in 8 to date | Story Points accepted in 9 to date | Story Points accepted in 10 to date | Story Points accepted in 11 to date | Story Points accepted in 12 to date | Developer/QA Count in Q2 | Total Story points Delivered across sprints in Q2 | # of Sprints in Q2 | Avg USP / SP in Q2 (SP 7 to 12) | Avg USP / Month In Q2(SP 7 to 12) | RAG (Q1 vs Q2 Δ) | AVG SP in Q1 with 4 SP | RAG Q1(4SP) vs Q2 Δ | Story Points accepted in 13 to date | Story Points accepted in 14 to date | Story Points accepted in 15 to date | Story Points accepted in 16 to date | Story Points accepted in 17 to date | Story Points accepted in 18 to date | Story Points accepted in 18 to date | Developer/QA Count in Q2 | Total Story points Delivered across sprints in Q2 | # of Sprints in Q2 | Avg USP / SP in Q3 (SP 13 to 15) | Avg USP / Month In Q3(SP 13 to 15)
IXT | CEUI | Assisted Tools | CPOS | Yes | [11 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 28 | 22 | 39 | 6 | 89 | 3 | 29.6667 | 59.3333 | 6 | 89 | 3 | 29.6667 | 59.3333 | 13 | 27 | 33 | 22 | 12 | 42 | 4 | 149 | 6 | 24.8333 | 49.6667 | 29 | 23 | 14 | 13 | 27 | 32 | 4 | 138 | 6 | 23 | 46 | ▼ 1.83 | 23.75 | ▼ 0.75 | 32 | 29 | [5 empty] | 4 | 61 | 2 | 30.5 | 61
IXT | CEUI | Assisted Tools | Xumo | Yes | 67 | 74 | 75 | 55 | 7 | 49 | 54 | 6 | 54 | 56 | 6 | 6.5 | 356 | 6 | 59.3333 | 118.6667 | 59 | 53 | 6.5 | 52 | 67 | 69 | 55 | 24 | 6.5 | 385.5 | 7 | 55.0714 | 110.1429 | 6.5 | 863 | 15 | 57.5333 | 115.0667 | 43 | 40 | 46 | 52 | 49 | 52 | 5.5 | 282 | 6 | 47 | 94 | 50 | 53 | 53 | 52 | 53 | 59 | 5 | 320 | 6 | 53.3333 | 106.6667 | ▲ 6.33 | 45.25 | ▲ 8.08 | 54 | 69 | 51 |  |  |  |  | 5 | 174 | 3 | 58 | 116
IXT | CEUI | Platform | Flow Engine (prometheus) | Yes | 28 | 28 | 20 | 26 | 9 | 30 | 27 | 9 | 22 | 39 | 9 | 9 | 182 | 6 | 30.3333 | 60.6667 | 35 | 45 | 9 | 36 | 32 | 36.5 | 35.5 | 46 | 9 | 275 | 7 | 39.2857 | 78.5714 | 9 | 486 | 15 | 32.4 | 64.8 | 27 | 39 | 36 | 39 | 38 | 32 | 9 | 211 | 6 | 35.1667 | 70.3333 | 37 | 34 | 37 | 44 | 48 | 48.5 | 9 | 248.5 | 6 | 41.4167 | 82.8333 | ▲ 6.25 | 35.25 | ▲ 6.17 | 45 | 50 | 51 |  |  |  |  | 9 | 146 | 3 | 48.6667 | 97.3333
IXT | CEUI | Platform | Flow Engine (optimus) | Yes | 8.5 | 8 | 10.5 | 10 | 2 | 8.5 | 8 | 2 | 6.5 | 9.5 | 2 | 2 | 57 | 6 | 9.5 | 19 | 8.5 | 8 | 2 | 7 | 10 | 9 | 8.5 | 8 | 2 | 61 | 7 | 8.7143 | 17.4286 | 2 | 128.5 | 15 | 8.5667 | 17.1333 | 6.5 | 8.5 | 9.5 | 10 | 12 | 6.5 | 2 | 53 | 6 | 8.8333 | 17.6667 | 8.5 | 8 | 9 | 10 | 8 | 8 | 2 | 51.5 | 6 | 8.5833 | 17.1667 | ▼ 0.25 | 8.625 | ▼ 0.04 | 6.5 | 10 | 10.5 |  |  |  |  | 2 | 27 | 3 | 9 | 18
IXT | CEUI | Platform | Celestial (Titan) | Yes | 47 | 43 | 60 | 75 | 6 | 80 | 47 | 6 | 82 | 67 | 6 | 5 | 423 | 6 | 70.5 | 141 | 56 | 57 | 5 | 54 | 50 | 60 | 55 | 36 | 5 | 373 | 7 | 53.2857 | 106.5714 | 5 | 869 | 15 | 57.9333 | 115.8667 | 57 | 65 | 63 | 60 | 62 | 67 | 5 | 374 | 6 | 62.3333 | 124.6667 | 64 | 71 | 66 | 70 | 60 | 60 | 5 | 391 | 6 | 65.1667 | 130.3333 | ▲ 2.83 | 61.25 | ▲ 3.92 | 66 | 56 | 60 |  |  |  |  | 4 | 182 | 3 | 60.6667 | 121.3333
IXT | CEUI | Platform | Celestial (Universal) | Yes | 42 | 38 | 44 | 51 | 6 | 49 | 48 | 6 | 35 | 50 | 6 | 7 | 289 | 6 | 48.1667 | 96.3333 | 58 | 55 | 7 | 58 | 50 | 52 | 53 | 65 | 7 | 398 | 7 | 56.8571 | 113.7143 | 7 | 748 | 15 | 49.8667 | 99.7333 | 63 | 58 | 64 | 68 | 62 | 66 | 7 | 381 | 6 | 63.5 | 127 | 63 | 65 | 64 | 67 | 71 | 67 | 7 | 397 | 6 | 66.1667 | 132.3333 | ▲ 2.67 | 63.25 | ▲ 2.92 | 74 | 69 | 71 |  |  |  |  | 7 | 214 | 3 | 71.3333 | 142.6667
IXT | CEUI | Platform | Right Answers | Yes | 17 | 18 | 15 | 17 | 2 | 18 | 18 | 2 | 17 | 26 | 2 | 2 | 115 | 6 | 19.1667 | 38.3333 | 18 | 15 | 2 | 10 | 7 | 13 | 8 | 12 | 2 | 85 | 7 | 12.1429 | 24.2857 | 2 | 229 | 15 | 15.2667 | 30.5333 | 6 | 9 | 4 | 4 | 22 | 20 | 2 | 65 | 6 | 10.8333 | 21.6667 | 23 | 25 | 11 | 21 | 19 | 21 | 2 | 120 | 6 | 20 | 40 | ▲ 9.17 | 5.75 | ▲ 14.25 | 22 | 18 | 20 |  |  |  |  | 2 | 60 | 3 | 20 | 40
IXT | CEUI | Assisted Tools | XM360 CBM/Phoenix | Yes | 27 | 30 | 21 | 63 | 7 | 24 | 55 | 7 | 35 | 57 | 7 | 8 | 269 | 6 | 44.8333 | 89.6667 | 67 | 66 | 8 | 63 | 78 | 60 | 39 | 41 | 8 | 422 | 7 | 60.2857 | 120.5714 | 8 | 726 | 15 | 48.4 | 96.8 | 30 | 58 | 68 | 81 | 59 | 61 | 8 | 357 | 6 | 59.5 | 119 | 58 | 41 | 51 | 41 | 39 | 49 | 8 | 279 | 6 | 46.5 | 93 | ▼ 13.00 | 59.25 | ▼ 12.75 | 41 | 47 | 39 |  |  |  |  | 8 | 127 | 3 | 42.3333 | 84.6667
IXT | CEUI | Assisted Tools | XM360 Recovery/Reliability | No | 55 | 50 | 51 | 43 | 8 | 45 | 44 | 8 | 28 | 38 | 6.5 | 6.5 | 265 | 6 | 44.1667 | 88.3333 | 45 | 52 | 6.5 | 59 | 55 | 51 | 50 | 45 | 6.5 | 363.5 | 7 | 51.9286 | 103.8571 | 6.5 | 711 | 15 | 47.4 | 94.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [12 empty] | 0
IXT | CEUI | Assisted Tools | XM360 Supersonix | Yes | 27 | 39 | 58 | 43 | 7.5 | 45 | 47 | 7.5 | 28 | 22 | 4.5 | 4.5 | 258 | 6 | 43 | 86 | 28 | 32 | 4.5 | 39 | 47 | 33 | 27 | 29 | 4.5 | 239.5 | 7 | 34.2143 | 68.4286 | 4.5 | 544 | 15 | 36.2667 | 72.5333 | 27 | 62 | 66 | 57 | 79 | 75 | 8 | 366 | 6 | 61 | 122 | 59 | 66 | 70 | 75 | 51 | 38 | 8 | 359 | 6 | 59.8333 | 119.6667 | ▼ 1.17 | 53 | ▲ 6.83 | 42 | 43 | 44 |  |  |  |  | 8 | 129 | 3 | 43 | 86
IXT | CEUI | Assisted Tools | XM Velocity 1/Xceeders | Yes | 11 | 41 | 20 | 16 | 6.5 | 42 | 22 | 6.5 | 29 | 36 | 6.5 | 6.5 | 178 | 6 | 29.6667 | 59.3333 | 46 | 41 | 6.5 | 20 | 46 | 37 | 42 | 26 | 6.5 | 264.5 | 7 | 37.7857 | 75.5714 | 6.5 | 475 | 15 | 31.6667 | 63.3333 | 45 | 49 | 44 | 55 | 41 | 47 | 6.5 | 281 | 6 | 46.8333 | 93.6667 | 38 | 38 | 37 | 59 | 49 | 54 | 6.5 | 275 | 6 | 45.8333 | 91.6667 | ▼ 1.00 | 48.25 | ▼ 2.42 | 64 | 99 | 96 |  |  |  |  | 11 | 259 | 3 | 86.3333 | 172.6667
IXT | CEUI | Assisted Tools | XM Velocity 2/Xplorers | Yes | 24 | 67 | 40 | 14 | 7.5 | 25 | 25 | 7.5 | 32 | 35 | 7.5 | 7.5 | 186 | 6 | 31 | 62 | 39 | 21 | 7.5 | 29 | 38 | 32 | 34 | 29 | 7.5 | 229.5 | 7 | 32.7857 | 65.5714 | 7.5 | 484 | 15 | 32.2667 | 64.5333 | 46 | 37 | 36 | 47 | 26 | 47 | 7.5 | 239 | 6 | 39.8333 | 79.6667 | 41 | 36.5 | 29 | 51 | 55 | 46 | 6 | 258.5 | 6 | 43.0833 | 86.1667 | ▲ 3.25 | 41.5 | ▲ 1.58 | [7 empty] | 6 | 0 | 3 | 0 | 0
IXT | Field experience | Field Experience | NWT - UI | Yes | 82 | 58 | 69 | 66 | 8.5 | 76 | 70 | 8.5 | 70 | 92 | 8.5 | 8.5 | 460 | 6 | 76.6667 | 153.3333 | 50 | 78 | 8.5 | 56 | 63 | 68 | 59 | 54 | 8.5 | 436.5 | 7 | 62.3571 | 124.7143 | 8.5 | 1011 | 15 | 67.4 | 134.8 | 63 | 43 | 72 | 63 | 51 | 42 | 8.5 | 334 | 6 | 55.6667 | 111.3333 | 39 | 48 | 37 | 67 | 30 | 44 | 5 | 265 | 6 | 44.1667 | 88.3333 | ▼ 11.50 | 60.25 | ▼ 16.08 | 35 | 55 | 65 |  |  |  |  | 6.5 | 155 | 3 | 51.6667 | 103.3333
IXT | Field experience | Field Experience | NWT-FSM | Yes |  |  |  | 23 | 3.5 | 17 | 20 | 3.5 | 14 | 20 | 3.5 | 3.5 | 101 | 5 | 20.2 | 40.4 | 27 | 20 | 3.5 | 10 | 16 | 18 | 10 | 24 | 3.5 | 128.5 | 7 | 18.3571 | 36.7143 | 3.5 | 219 | 12 | 18.25 | 36.5 | 6 | 16 | 16 | 21 | 22 | 17 | 3.5 | 98 | 6 | 16.3333 | 32.6667 | 23 | 21 | 16 | 24 | 17 | 27 | 2.5 | 128 | 6 | 21.3333 | 42.6667 | ▲ 5.00 | 14.75 | ▲ 6.58 | 25 | 39 | 38 |  |  |  |  | 4.5 | 102 | 3 | 34 | 68
IXT | Field experience | Field Experience | NWT - PSNB | Yes | 17 | 21.5 | 15.5 | 19 | 2 | 17 | 16.5 | 2 | 14 | 19 | 2 | 2 | 105 | 6 | 17.5 | 35 | 14 | 21.5 | 2 | 15.5 | 18 | 27.3 | 18 | 7.5 | 2 | 123.8 | 7 | 17.6857 | 35.3714 | 2 | 261.3 | 15 | 17.42 | 34.84 | 20 | 14 | 17.5 | 11.5 | 16.5 | 9 | 2 | 88.5 | 6 | 14.75 | 29.5 | 17 | 12 | 11 | 9 | 11 | 10.5 | 2 | 70.5 | 6 | 11.75 | 23.5 | ▼ 3.00 | 15.75 | ▼ 4.00 | 11 | [6 empty] | 2 | 11 | 1 | 11 | 22
IXT | Field experience | Field Experience | NWT - Core | Yes | 93 | 88 | 85 | 91 | 10 | 92 | 79 | 10 | 78 | 88 | 10 | 10 | 533 | 6 | 88.8333 | 177.6667 | 62 | 72 | 10 | 91 | 88 | 90 | 89 | 76 | 10 | 578 | 7 | 82.5714 | 165.1429 | 10 | 1262 | 15 | 84.1333 | 168.2667 | 66 | 79 | 44 | 44 | 41 |  | 10 | 274 | 6 | 45.6667 | 91.3333 | 4 | 28 | 29 |  |  |  | 4.5 | 61 | 3 | 20.3333 | 40.6667 | ▼ 25.33 | 58.25 | ▼ 37.92 | [7 empty] | 4.5 | 0 | 3 | 0 | 0
IXT | Payment & Billing | XRM | XRM - VOIXM Scrum | Yes | 48 | 36 | 28 | 40 | 11 | 52 | 57 | 11 | 43 | 56 | 11 | 10 | 298 | 6 | 49.6667 | 99.3333 | 52 | 55 | 10 | 54 | 52 | 59 | 59 | 54 | 10 | 395 | 7 | 56.4286 | 112.8571 | 10 | 745 | 15 | 49.6667 | 99.3333 | 49 | 56 | 59 | 75 | 66 | 72 | 10 | 377 | 6 | 62.8333 | 125.6667 | 64 | 67 | 58 | 59 | 52 | 52 | 10 | 352 | 6 | 58.6667 | 117.3333 | ▼ 4.17 | 59.75 | ▼ 1.08 | 53 | 60 | 54 |  |  |  |  | 10 | 167 | 3 | 55.6667 | 111.3333
IXT | Payment & Billing | XRM | XRM - Video Scrum | Yes | 49 | 73 | 69 | 76 | 11 | 83 | 70 | 11 | 63 | 74 | 11 | 11 | 457 | 6 | 76.1667 | 152.3333 | 66 | 76 | 11 | 72 | 70 | 67 | 67 | 52 | 11 | 481 | 7 | 68.7143 | 137.4286 | 11 | 1027 | 15 | 68.4667 | 136.9333 | 65 | 62 | 82 | 79 | 71 | 65 | 11 | 424 | 6 | 70.6667 | 141.3333 | 68 | 61 | 58 | 69 | 78 | 75 | 10 | 409 | 6 | 68.1667 | 136.3333 | ▼ 2.50 | 72 | ▼ 3.83 | 78 | 77 | 78 |  |  |  |  | 11 | 233 | 3 | 77.6667 | 155.3333
IXT | Payment & Billing | XRM | XRM - HSD Scrum | Yes | 40 | 49 | 50 | 49 | 10 | 47 | 53 | 10 | 55 | 54 | 10 | 10 | 328 | 6 | 54.6667 | 109.3333 | 43 | 63 | 10 | 59 | 45 | 50 | 49 | 34 | 10 | 353 | 7 | 50.4286 | 100.8571 | 10 | 740 | 15 | 49.3333 | 98.6667 | 30 | 45 | 53 | 59 | 79 | 61 | 10 | 327 | 6 | 54.5 | 109 | 59 | 58.1 | 57 | 52 | 45 | 48 | 11 | 319.1 | 6 | 53.1833 | 106.3667 | ▼ 1.32 | 46.75 | ▲ 6.43 | 36 | 48 | 55 |  |  |  |  | 10 | 139 | 3 | 46.3333 | 92.6667
IXT | Payment & Billing | BXT | DevOps | Yes | 71 | 54 | 56 | 57 | 9 | 49 | 42 | 9 | 61 | 55 | 9 | 9 | 338 | 6 | 56.3333 | 112.6667 | 55 | 32 | 9 | 46 | 54 | 52 | 35 | 30 | 9 | 313 | 7 | 44.7143 | 89.4286 | 9 | 749 | 15 | 49.9333 | 99.8667 | 56 | 55 | 55 | 57 | 58 | 62 | 9 | 343 | 6 | 57.1667 | 114.3333 | 49 | 60 | 56 | 63 | 65 | 74 | 9 | 367 | 6 | 61.1667 | 122.3333 | ▲ 4.00 | 55.75 | ▲ 5.42 | 86 | 79 | [5 empty] | 9 | 165 | 2 | 82.5 | 165
IXT | CEUI | Assisted Tools | Einstein 360 | No | [5 empty] | 5 | 32 | 4 | 22 | 22 | 4 | 4 | 85 | 6 | 14.1667 | 28.3333 | 32 | 22 | 4 | 23 | 21 | 27 | 13 | 22 | 4 | 164 | 7 | 23.4286 | 46.8571 | 4 | 241 | 11 | 21.9091 | 43.8182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [12 empty] | 0
IXT | Payment & Billing | Account Services | Account Services - BRE | Yes | [11 empty] | 2 | 0 | 6 | 0 | 0 | 32 | 26 | 2 | 26 | 29 | 18 | 15 | 24 | 2 | 172 | 7 | 24.5714 | 49.1429 | 2 | 170 | 7 | 24.2857 | 48.5714 | 24 | 23 | 28 | 23 | 24 | 18 | 2 | 140 | 6 | 23.3333 | 46.6667 | 26 | 28 | 28 | 30 | 25 | 27 | 2 | 164 | 6 | 27.3333 | 54.6667 | ▲ 4.00 | 24.5 | ▲ 2.83 | 21 | 24 | 24 |  |  |  |  | 2 | 69 | 3 | 23 | 46
IXT | Payment & Billing | Account Services | Account Services - XM PDF | Yes | [11 empty] | 4 | 0 | 6 | 0 | 0 | 40 | 33 | 4 | 51 | 51 | 41 | 24 | 9 | 4 | 253 | 7 | 36.1429 | 72.2857 | 4 | 249 | 7 | 35.5714 | 71.1429 | 42 | 42 | 38 | 34 | 35 | 29 | 3 | 220 | 6 | 36.6667 | 73.3333 | 24 | 48 | 47 | 46 | 50 | 49 | 5 | 264 | 6 | 44 | 88 | ▲ 7.33 | 39 | ▲ 5.00 | 43 | 50 | 46 |  |  |  |  | 5 | 139 | 3 | 46.3333 | 92.6667
IXT | Payment & Billing | Account Services | Account Services - NOW | Yes | [11 empty] | 2 | 0 | 6 | 0 | 0 | 10 | 13 | 2 | 16 | 23 | 5 | 2 | 5 | 2 | 76 | 7 | 10.8571 | 21.7143 | 2 | 74 | 7 | 10.5714 | 21.1429 | NA | NA | NA | NA | 17 | 13 | 2 | 30 | 6 | 5 | 10 | 10 | [5 empty] | 1 | 10 | 1 | 10 | 20 | ▲ 5.00 | 0 | ▲ 10.00
IXT | Field experience | Field Experience | NWT-FSM 2 (NOVA) | Yes | [41 empty] | 0 | 6 | 0 | 0 | 10 | 27 | 8 | 17 | 15 | 7 | 2 | 84 | 6 | 14 | 28 | ▲ 14.00 | 0 | ▲ 14.00 | 14 | [6 empty] | 2 | 14 | 1 | 14 | 28
IXT | [45 empty] | 0 | 6 | 0 | 0
IXT | [45 empty] | 0 | 6 | 0 | 0
IXT | [45 empty] | 0 | 6 | 0 | 0
IXT | [45 empty] | 0 | 6 | 0 | 0
[46 empty] | 0 | 6 | 0 | 0

## Pivot Velocity
Workstream | - all -
Active App | Yes
Row Labels | USP / SP in Q4 (SP 20 to 26) | USP / SP in Q1 (SP 1 to 6) | USP / SP in Q2 (SP 7 to 12) | USP / SP in Q3 (SP 13 to 15)
Account Services | 71.5714 | 65 | 81.3333 | 69.3333
Assisted Tools | 249.8095 | 279 | 271.5833 | 260.1667
BXT | 44.7143 | 57.1667 | 61.1667 | 82.5
Field Experience | 180.9714 | 132.4167 | 111.5833 | 110.6667
Platform | 170.2857 | 180.6667 | 201.3333 | 209.6667
XRM | 175.5714 | 188 | 180.0167 | 179.6667
Total Result | 892.9238 | 902.25 | 907.0167 | 912

## Master Data Predictability
SL No | Domain | Workstream | QBR | Active App | Application/Area | Sprint 12 Predictability (# SP accepted in sp 12 / # SP planned into sprint 12) | Sprint 13 Predictability (# SP accepted in sp 13 at end of each sprint / # SP planned into sprint 13) | Sprint 14 Predictability (# SP accepted in sp 14 / # SP planned into sprint 14) | Sprint 15 Predictability (# SP accepted in sp 15 at end of each sprint / # SP planned into sprint 15) | Sprint 16 Predictability (# SP accepted in sp 16 / # SP planned into sprint 16) | Sprint 17 Predictability (# SP accepted in sp 17 at end of each sprint / # SP planned into sprint 17) | Sprint 18 Predictability (# SP accepted in sp 18 / # SP planned into sprint 18) | Sprint 19 Predictability (# SP accepted in sp 19 at end of each sprint / # SP planned into sprint 19) | Sprint 20 Predictability (# SP accepted in sp 20 / # SP planned into sprint 20) | Sprint 21 Predictability (# SP accepted in sp 21 at end of each sprint / # SP planned into sprint 21) | Sprint 22 Predictability (# SP accepted in sp 22 / # SP planned into sprint 22) | Sprint 23 Predictability (# SP accepted in sp 23 at end of each sprint / # SP planned into sprint 23) | Sprint 24 Predictability (# SP accepted in sp 24 at end of each sprint / # SP planned into sprint 24) | Sprint 25 Predictability (# SP accepted in sp 25 at end of each sprint / # SP planned into sprint 25) | Sprint 26 Predictability (# SP accepted in sp 26 at end of each sprint / # SP planned into sprint 26) | Avg Predictablity In 2025(SP 12 to 26) | Avg Predictablity In Q3(SP 14 to 19) | Avg Predictablity In Q4(SP 20 to 26) | Sprint 1 Predictability (# SP accepted in sp 1 / # SP planned into sprint 1) | Sprint 2 Predictability (# SP accepted in sp 2 / # SP planned into sprint 2) | Sprint 3 Predictability (# SP accepted in sp 3 / # SP planned into sprint 3) | Sprint 4 Predictability (# SP accepted in sp 4 / # SP planned into sprint 4) | Sprint 5 Predictability (# SP accepted in sp 5/ # SP planned into sprint 5) | Sprint 6 Predictability (# SP accepted in sp 6/ # SP planned into sprint 5) | Avg Predictablity In Q1(SP 1 to 6) | Sprint 7 Predictability (# SP accepted in sp 7 / # SP planned into sprint 7) | Sprint 8 Predictability (# SP accepted in sp 8 / # SP planned into sprint 8) | Sprint 9 Predictability (# SP accepted in sp 9 / # SP planned into sprint 9) | Sprint 10 Predictability (# SP accepted in sp 10 / # SP planned into sprint 10) | Sprint 11 Predictability (# SP accepted in sp 11 / # SP planned into sprint 11) | Sprint 12 Predictability (# SP accepted in sp 12 at end of each sprint / # SP planned into sprint 12 ) | Avg Predictablity In Q2(SP 7 to 12) | Sprint 13 Predictability (# SP accepted in sp 13 / # SP planned into sprint 13) | Sprint 14 Predictability (# SP accepted in sp 14 / # SP planned into sprint 14) | Sprint 15 Predictability (# SP accepted in sp 15 / # SP planned into sprint 15) | Sprint 16 Predictability (# SP accepted in sp 16 / # SP planned into sprint 16) | Sprint 17 Predictability (# SP accepted in sp 17 / # SP planned into sprint 17) | Sprint 18 Predictability (# SP accepted in sp 18 at end of each sprint / # SP planned into sprint 18 ) | Sprint 19 Predictability (# SP accepted in sp 19 at end of each sprint / # SP planned into sprint 19 ) | Avg Predictablity In Q3(SP 13 to 15)
1 | IXT | CEUI | Assisted Tools | Yes | CPOS | [12 empty] | 467% | 169% | 89% | 241.7% |  | 241.7% | 39% | 104% | 132% | 67% | 28% | 466.7% | 139.4% | 207.1% | 58.97% | 61% | 54% | 67.5% |  | 89.72% | 86% | 91% | [5 empty] | 88.5%
2 | IXT | CEUI | Assisted Tools | Yes | Xumo | 113.6% | 132.1% | 110.3% | 88.71% | 84.48% | 103.8% | 96.43% | 100% | 92.19% | 89.83% | 96% | 105% | 104.5% | 94.83% | 54.55% | 97.76% | 97.29% | 90.99% | 116% | 98% | 115% | 111% | 120% | 121% | 113.5% | 116.3% | 120.5% | 113% | 111% | 106% |  | 113.3% | 117% | 138% | [5 empty] | 127.5%
3 | IXT | CEUI | Platform | Yes | Flow Engine (prometheus) | 75.68% | 91.43% | 55.56% | 65% | 81.08% | 69% | 57% | 61% | 70% | 83% | 75% | 67% | 90.12% | 79.78% | 68.15% | 72.59% | 64.77% | 76.15% | 52% | 85% | 84% | 78% | 86% | 70% | 75.83% | 86.05% | 82.93% | 84% | 89% | 84.96% | 94.17% | 86.85% | 96% | 98% | [5 empty] | 97%
4 | IXT | CEUI | Platform | Yes | Flow Engine (optimus) | 188.9% | 114.3% | 215.8% | 357.1% | 566.7% | 442.8% | 566.7% | 440% | 567% | 533% | 140% | 200% | 150% | 141.7% | 133.3% | 317.1% | 431.5% | 266.4% | 325% | 71% | 146% | 143% | 1200% | 163% | 341.3% | 121.4% | 123.1% | 106% | 333% | 106.7% |  | 158% | 76% | 95% | 81% |  |  |  |  | 84%
5 | IXT | CEUI | Platform | Yes | Celestial (Titan) | 78.33% | 87.76% | 84.51% | 102.7% | 98.77% | 72.31% | 97.62% | 94.37% | 100% | 104% | 100% | 83% | 111.1% | 100% | 100% | 94.3% | 91.72% | 99.73% | 100% | 100% | 109% | 100% | 100% | 100% | 101.5% | 95.52% | 100% | 100% | 103% | 92.31% | 92.31% | 97.19% | 100% | 100% | 100% |  |  |  |  | 100%
6 | IXT | CEUI | Platform | Yes | Celestial (Universal) | 85.71% | 86.36% | 100% | 106.2% | 108.9% | 81.36% | 92.11% | 100% | 100% | 89% | 98.31% | 93% | 98.11% | 88.33% | 98.48% | 95.06% | 98.1% | 95.03% | 100% | 98% | 103% | 121% | 100% | 96% | 103% | 100% | 97.01% | 100% | 99% | 106% | 100% | 100.3% | 107% | 101% | 97% |  |  |  |  | 101.7%
7 | IXT | CEUI | Platform | Yes | Right Answers | 80.95% | 100% | 88.24% | 89.47% | 100% | 72% | 68% | 89.66% | 78.26% | 68.18% | 58.82% | 25% | 65% | 42.11% | 75% | 73.38% | 84.56% | 58.91% | 67% | 56% | 100% | 44% | 100% | 87% | 75.67% | 109.5% | 86.21% | 69% | 100% | 126.7% | 140% | 105.2% | 100% | 120% | 100% |  |  |  |  | 106.7%
8 | IXT | CEUI | Assisted Tools | Yes | XM360 CBM/Phoenix | 93.1% | 40% | 28% | 94.03% | 75% | 80.88% | 60.34% | 79.17% | 128.8% | 111.9% | 103.3% | 128% | 101.7% | 125.8% | 110.8% | 90.72% | 69.57% | 115.8% | 100% | 116% | 111% | 133% | 89% | 139% | 114.7% | 116% | 97.62% | 124% | 103% | 111.4% | 122.5% | 112.4% | 137% | 102% | 93% |  |  |  |  | 110.7%
9 | IXT | CEUI | Assisted Tools | No | XM360 Recovery/Reliability | 177.4% | 89.29% | 115.9% | 126.5% | 104.7% | 137.5% | 87.5% | 88.37% | 95.74% | 94.55% | 105.4% | 100% | 102% | 104.2% | 100% | 108.6% | 110.1% | 100.3% | [6 empty] | 0% | [6 empty] | 0%
10 | IXT | CEUI | Assisted Tools | Yes | XM360 Supersonix | 64.29% | 92.86% | 141.5% | 100% | 100% | 104.4% | 100% | 56.41% | 107.7% | 100% | 150% | 134% | 113.8% | 117.4% | 103.6% | 105.7% | 100.4% | 118.1% | 100% | 100% | 99% | 130% | 127% | 174% | 121.7% | 143.9% | 137.5% | 149% | 150% | 175.9% | 108.6% | 144.1% | 120% | 143% | 129% |  |  |  |  | 130.7%
11 | IXT | CEUI | Assisted Tools | Yes | XM Velocity 1/Xceeders | 17.46% | 55.41% | 76.92% | 38.1% | 105% | 51.16% | 70.73% | 75% | 95.83% | 128.1% | 100% | 102% | 86.05% | 91% | 57.78% | 76.7% | 69.49% | 94.4% | 90% | 82% | 92% | 141% | 117% | 115% | 106.2% | 200% | 100% | 116% | 137% | 104.3% | 128.6% | 131% | 160% | 132% | [5 empty] | 146%
12 | IXT | CEUI | Assisted Tools | Yes | XM Velocity 2/Xplorers | 32% | 91.78% | 148.1% | 31.11% | 51.02% | 67.57% | 76.19% | 63.64% | 78% | 56.76% | 96.67% | 95% | 68.09% | 113% | 85.29% | 76.95% | 72.95% | 84.69% | 112% | 106% | 106% | 131% | 87% | 134% | 112.7% | 186.4% | 125.9% | 100% | 138% | 98.21% | 77.97% | 121.1% | [7 empty] | 0%
13 | IXT | Field experience | Field Experience | Yes | NWT - UI | 115.5% | 79.45% | 100% | 103% | 109% | 101% | 159% | 177% | 139% | 83% | 76% | 66% | 86.08% | 71.08% | 78.26% | 102.9% | 124.8% | 85.63% | 107% | 86% | 96% | 88% | 73% | 69% | 86.5% | 78% | 72.73% | 71% | 122% | 62.5% |  | 81.25% | 70% | 90% | 112% |  |  |  |  | 90.67%
14 | IXT | Field experience | Field Experience | Yes | NWT-FSM |  |  |  | 100% | 85% | 118% | 127% | 100% | 113% | 143% | 100% | 84% | 128.6% | 100% | 96% | 107.9% | 106% | 109.2% | 100% | 100% |  | 150% | 81% | 89% | 104% | 76.67% | 95.45% | 76% | 126% | 89.47% |  | 92.72% | 93% | 355% | 271% |  |  |  |  | 239.7%
15 | IXT | Field experience | Field Experience | Yes | NWT - PSNB | 94.44% | 100% | 73.81% | 95% | 106% | 100% | 78% | 100% | 108% | 110% | 84% | 109% | 164.5% | 171.4% | 88.24% | 105.5% | 92.13% | 119.3% | 148% | 97% | 85% | 70% | 103% | 82% | 97.5% | 106.2% | 70.59% | 85% | 64% | 91.67% |  | 83.5% | 122% | [6 empty] | 122%
16 | IXT | Field experience | Field Experience | Yes | NWT - Core | 98.94% | 117.3% | 102.4% | 107% | 108% | 104% | 101% | 113% | 94% | 109% | 130% | 104% | 100% | 100% | 102.7% | 106.1% | 105.9% | 105.7% | 93% | 176% | 122% | 105% | 100% |  | 119.2% | 100% | 100% | 94% | 97% |  |  | 97.75%
17 | IXT | Payment & Billing | XRM | Yes | XRM - VOIXM Scrum | 94.12% | 105.9% | 90.62% | 113.5% | 92.86% | 91.94% | 91.49% | 91.8% | 106% | 95% | 104% | 96% | 103.5% | 100% | 100% | 98.45% | 95.37% | 100.6% | 123% | 104% | 98% | 101% | 100% | 100% | 104.3% | 110.3% | 100% | 102% | 92% | 100% | 100% | 100.7% | 96% | 100% | 100% |  |  |  |  | 98.67%
18 | IXT | Payment & Billing | XRM | Yes | XRM - Video Scrum | 245% | 98.65% | 90.79% | 97.44% | 98.81% | 97.22% | 91.3% | 93.67% | 100% | 99% | 104% | 99% | 101.5% | 93.06% | 88.14% | 106.5% | 94.87% | 97.82% | 100% | 100% | 103% | 100% | 99% | 100% | 100.3% | 98.55% | 89.71% | 92% | 97% | 97.5% | 91.46% | 94.37% | 96% | 90% | 93% |  |  |  |  | 93%
19 | IXT | Payment & Billing | XRM | Yes | XRM - HSD Scrum | 97.32% | 87.5% | 92% | 100% | 88.68% | 100% | 93.22% | 103.8% | 93% | 94% | 92% | 71% | 94.34% | 85.96% | 94.44% | 92.49% | 96.29% | 89.25% | 97% | 88% | 102% | 95% | 103% | 90% | 95.83% | 105.4% | 90.64% | 97% | 93% | 81.82% | 114.3% | 97.02% | 97% | 98% | 102% |  |  |  |  | 99%
20 | IXT | Payment & Billing | BXT | Yes | DevOps | 131.5% | 83.08% | 78.87% | 81.43% | 90.74% | 77.78% | 1.0167 | 0.94828 | 0.94828 | 0.94118 | 0.86 | 96% | 91% | 90% | 73% | 90.99% | 87.55% | 89.28% | 98% | 100% | 96% | 88% | 105% | 100% | 97.83% | 100% | 92.31% | 88% |  | 100% |  | 95.08% | 100% | 93% | [5 empty] | 96.5%
21 | IXT | CEUI | Assisted Tools | No | Einstein 360 |  |  |  |  | 26.32% | 128% | 122.2% | 104.8% | 106.7% | 100% | 86% | 210% | 270% | 118.2% | 200% | 133.8% | 95.32% | 155.8% | [13 empty] | 0%
22 | IXT | Payment & Billing | Account Services | Yes | Account Services - BRE | [8 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 88% | 100% | 100% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% |  |  |  |  | 98.33%
23 | IXT | Payment & Billing | Account Services | Yes | Account Services - XM PDF | [8 empty] | 100% | 100% | 212.5% | 104% | 164% | 0% | 100% | 111.5% |  | 111.5% | 100% | 100% | 100% | 103% | 100% | 100% | 100.5% | 100% | 133.3% | 100% | 100% | 100% | 100% | 105.6% | 84% | 100% | 82% |  |  |  |  | 88.67%
24 | IXT | Payment & Billing | Account Services | Yes | Account Services - NOW | [25 empty] | 100% | [5 empty] | 100%
25 | IXT | Field experience | Field Experience | Yes | NWT-FSM | [26 empty] | 200% | 38% | 106% | 93.75% |  | 109.4% | 93% | [6 empty] | 93%
Note on O23: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on O24: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on P23: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on P24: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on Q23: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on Q24: Formula previously referenced an external workbook ('[1]Base data Velocity') that is not available in this file, so it could not be recalculated. Replaced with the last known value from the source file. Re-link to the source workbook if it becomes available.
Note on AH26: Salian, Bharat: Earlier it was 100%

## Pivot Predictability
Workstream | - all -
Active App | Yes
Row Labels | Q4 (SP 20 to 26) | Q1 (SP 1 to 6) | Q2(SP 7 to 12) | Q3(SP 13 to 15)
Account Services | 105.8% | 99.25% | 101.9% | 93.5%
Assisted Tools | 124.3% | 118% | 118.6% | 100.6%
BXT | 89.28% | 97.83% | 95.08% | 96.5%
Field Experience | 105% | 101.8% | 92.93% | 136.3%
Platform | 119.3% | 139.5% | 109.5% | 97.87%
XRM | 95.9% | 100.2% | 97.37% | 96.89%
Total Result | 111.9% | 114.7% | 105.1% | 105.3%

## Master PRD Defect Density %
Domain | Workstream | QBR | Application/Area | Active App | Sp 1 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 Jan / total story points delivered or accepted in sp 1) | Sp 2 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 Jan / total story points delivered or accepted in sp 2) | Sp 3 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 Feb / total story points delivered or accepted in sp 3) | Sp 4 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 FEb / total story points delivered or accepted in sp 4) | Sp 5 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 Mar / total story points delivered or accepted in sp 5) | Sp 6 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 Mar / total story points delivered or accepted in sp 6) | Avg PRD Defect Density % Q1 (SP 1 to 6) | Sp 7 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 Apr / total story points delivered or accepted in sp 7) | Sp 8 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 Apr / total story points delivered or accepted in sp 8) | Sp 9 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 May / total story points delivered or accepted in sp 9) | Sp 10 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 May / total story points delivered or accepted in sp 10) | Sp 11 PRD Defect Density % (# defect identified post- production within 23 days of release in H1 May / total story points delivered or accepted in sp 11) | Sp 12 PRD Defect Density % (# defect identified post- production of release within 23 days of release in H2 May / total story points delivered or accepted in sp 12) | Avg PRD Defect Density % Q2 (SP 7 to 12)
IXT | CEUI | Assisted Tools | CPOS | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% |  | 2.222%
IXT | CEUI | Assisted Tools | Xumo | Yes | 0% | 0% | 0% | 0% | 2.041% | 2.128% | 0.6947% | 0% | 0% | 0% | 0% | 0% |  | 0%
IXT | CEUI | Platform | Flow Engine (prometheus) | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.703% | 2.941% | 8.108% | 2.273% | 2.083% | 2.062% | 3.362%
IXT | CEUI | Platform | Flow Engine (optimus) | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
IXT | CEUI | Platform | Celestial (Titan) | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | CEUI | Platform | Celestial (Universal) | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.408% | 1.493% | 0.4835%
IXT | CEUI | Platform | Right Answers | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | CEUI | Assisted Tools | XM360 CBM/Phoenix | Yes | 10% | 3.448% | 0% | 0% | 0% | 0% | 2.241% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | CEUI | Assisted Tools | XM360 Recovery/Reliability | No
IXT | CEUI | Assisted Tools | XM360 Supersonix | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.085% | 0% | 0% | 4% | 9.804% | 10.53% | 4.902%
IXT | CEUI | Assisted Tools | XM Velocity 1/Xceeders | Yes | 0% | 0% | 4.545% | 12.73% | 14.63% | 8.511% | 6.736% | 7.895% | 5.263% | 3% | 2% | 2.041% | 1.852% | 3.675%
IXT | CEUI | Assisted Tools | XM Velocity 2/Xplorers | Yes | 0% | 2.703% | 5.556% | 0% | 15.38% | 10.64% | 5.714% | 7.317% | 5.479% | 0% | 6% | 0% | 2.174% | 3.495%
IXT | Field experience | Field Experience | NWT - UI | Yes | 0% | 0% | 0% | 0% | 1.961% | 0% | 0.3268% | 0% | 0% | 0% | 0% | 0% |  | 0%
IXT | Field experience | Field Experience | NWT-FSM | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
IXT | Field experience | Field Experience | NWT - PSNB | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
IXT | Field experience | Field Experience | NWT - Core | Yes | 4.545% | 0% | 0% | 0% | 0% |  | 0.9091% | 0% | 0% | 0% | 0% |  |  | 0%
IXT | Payment & Billing | XRM | XRM - VOIXM Scrum | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | Payment & Billing | XRM | XRM - Video Scrum | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | Payment & Billing | XRM | XRM - HSD Scrum | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | Payment & Billing | BXT | DevOps | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 0%
IXT | CEUI | Assisted Tools | Einstein 360 | No
IXT | Payment & Billing | Account Services | Account Services - BRE | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | Payment & Billing | Account Services | Account Services - XM PDF | Yes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
IXT | Payment & Billing | Account Services | Account Services - NOW | Yes |  |  |  |  | 0% | 0% | 0% | 0% | [5 empty] | 0%
IXT | Field experience | Field Experience | NWT-FSM 2 (NOVA) | Yes | [7 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%

## Pivot PRD Defect Density
Active App | Yes
Row Labels | Average of Avg PRD Defect Density % Q1 (SP 1 to 6) | Average of Avg PRD Defect Density % Q2 (SP 7 to 12)
CEUI | 1.399% | 1.649%
Field experience | 0.309% | 0%
Payment & Billing | 0% | 0%
Total Result | 0.7555% | 0.7887%

## Master Defects
Domain | Workstream | QBR | Application/Area | Active App | Count of all Defects for Sp 1 | Count of all Defects for Sp 2 | Count of all Defects for Sp 3 | Count of all Defects for Sp 4 | Count of all Defects for Sp 5 | Count of all Defects for Sp 6 | Avg Count of all Defects for Q1 (SP 1 to 6) | Count of all Defects for Sp 7 | Count of all Defects for Sp 8 | Count of all Defects for Sp 9 | Count of all Defects for Sp 10 | Count of all Defects for Sp 11 | Count of all Defects for Sp 12 | Avg Count of all Defects for Q2 (SP 7 to 12)
IXT | CEUI | Assisted Tools | CPOS | Yes | 3 | 11 | 2 | 0 | 2 | 0 | 3 | 4 | 5 | 3 | 4 | 6 |  | 4.4
IXT | CEUI | Assisted Tools | Xumo | Yes | 0 | 0 | 0 | 0 | 1 | 1 | 0.33333 | 0 | 0 | 0 | 0 | 0 |  | 0
IXT | CEUI | Platform | Flow Engine (prometheus) | Yes | 27 | 9 | 19 | 15 | 31 | 13 | 19 | 3 | 2 | 7 | 10 | 16 | 11 | 8.1667
IXT | CEUI | Platform | Flow Engine (optimus) | Yes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
IXT | CEUI | Platform | Celestial (Titan) | Yes | 2 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0.16667
IXT | CEUI | Platform | Celestial (Universal) | Yes | 2 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 3 | 1 | 1.1667
IXT | CEUI | Platform | Right Answers | Yes | 0 | 0 | 0 | 0 | 1 | 1 | 0.33333 | 2 | 0 | 2 | 0 | 0 | 0 | 0.66667
IXT | CEUI | Assisted Tools | XM360 CBM/Phoenix | Yes | 5 | 7 | 9 | 24 | 28 | 81 | 25.6667 | 22 | 7 | 3 | 8 | 8 | 8 | 9.3333
IXT | CEUI | Assisted Tools | XM360 Recovery/Reliability | No | [6 empty] | 0 | [6 empty] | 0
IXT | CEUI | Assisted Tools | XM360 Supersonix | Yes | 4 | 2 | 12 | 5 | 5 | 19 | 7.8333 | 17 | 8 | 14 | 12 | 33 | 19 | 17.1667
IXT | CEUI | Assisted Tools | XM Velocity 1/Xceeders | Yes | 6 | 18 | 19 | 21 | 18 | 9 | 15.1667 | 10 | 13 | 9 | 15 | 11 | 15 | 12.1667
IXT | CEUI | Assisted Tools | XM Velocity 2/Xplorers | Yes | 3 | 4 | 10 | 8 | 9 | 14 | 8 | 8 | 9 | 3 | 11 | 10 | 14 | 9.1667
IXT | Field experience | Field Experience | NWT - UI | Yes | 6 | 4 | 6 | 3 | 1 | 2 | 3.6667 | 4 | 3 | 4 | 0 | 3 |  | 2.8
IXT | Field experience | Field Experience | NWT-FSM | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
IXT | Field experience | Field Experience | NWT - PSNB | Yes | 4 | 3 | 3 | 1 | 1 | 1 | 2.1667 | 1 | 1 | 1 | 1 | 2 |  | 1.2
IXT | Field experience | Field Experience | NWT - Core | Yes | 0 | 0 | 2 | 0 | 0 |  | 0.4 | 0 | 0 | 0 | 0 | 0 |  | 0
IXT | Payment & Billing | XRM | XRM - VOIXM Scrum | Yes | 0 | 2 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IXT | Payment & Billing | XRM | XRM - Video Scrum | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IXT | Payment & Billing | XRM | XRM - HSD Scrum | Yes | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IXT | Payment & Billing | BXT | DevOps | Yes | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
IXT | CEUI | Assisted Tools | Einstein 360 | No | [6 empty] | 0 | [6 empty] | 0
IXT | Payment & Billing | Account Services | Account Services - BRE | Yes | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0
IXT | Payment & Billing | Account Services | Account Services - XM PDF | Yes | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0
IXT | Payment & Billing | Account Services | Account Services - NOW | Yes | [6 empty] | 0 | [6 empty] | 0
IXT | Agile Portfolio Mgmt | [16 empty] | 0
IXT | Agile Portfolio Mgmt | [16 empty] | 0
IXT | Field experience | Field Experience | NWT-FSM 2 (NOVA) | Yes | [9 empty] | 0 | 0 | 0 |  | 0
IXT
IXT
IXT
IXT

## Pivot Defects
Active App | Yes
Row Labels | Q1 (SP 1 to 6) | Q2 (SP 7 to 12)
CEUI | 7.3939 | 5.6727
Field experience | 1.5583 | 0.8
Payment & Billing | 0.21429 | 0
Total Result | 4.0485 | 2.887

## Review4
Month | Productivity | Velocity | Billable FTE | FTE contributing to SP | Productivity (audit calc: Velocity/FTE contributing/divisor) | Period Coverage
Oct’25 | 7.2197 | 1748 | 189 | 131 | 6.6718 | Full month
Nov’25 | 7.1145 | 1747 | 189 | 131 | 6.6679 | Full month
Dec’25 | 6.8252 | 2664.8 | 189 | 131 | 6.7807 | Full month
Jan’26 | 6.6981 | 1672 | 155 | 131 | 6.3817 | Full month
Feb’26 | 7.7395 | 1895.5 | 155 | 131 | 7.2347 | Full month
Mar’26 | 7.2578 | 1846 | 155 | 115 | 8.0261 | Full month
Apr’26 | 7.6514 | 1782.1 | 156 | 115 | 7.7483 | Full month
May’26 | 7.6967 | 1785 | 156 | 115 | 7.7609 | Full month
Jun’26 | 7.4723 | 868 | 156 | 115 | 7.5478 | Partial month (reduced divisor)
Note on B1: DATA QUALITY FLAG: This column contains hardcoded values, not live formulas, and it does not match the formula-based 'Productivity' figure in column F for the same month (e.g. Oct'25: 7.22 here vs 6.67 in column F, an ~8% gap). Confirm which definition of Productivity is correct before this is used as the headline number. See Data Quality Flags tab.

## Review5
Month | Velocity | Billable FTE | FTE contributing to SP | Productivity | Productivity divisor | Period Coverage
Oct’25 | 1748 | 189 | 131 | 6.6718 | 2 | Full month
Nov’25 | 1747 | 189 | 131 | 6.6679 | 2 | Full month
Dec’25 | 2664.8 | 189 | 131 | 6.7807 | 3 | Non-standard divisor (3) — reason undocumented
Jan’26 | 1672 | 155 | 131 | 6.3817 | 2 | Full month
Feb’26 | 1895.5 | 155 | 131 | 7.2347 | 2 | Full month
Mar’26 | 1846 | 155 | 115 | 8.0261 | 2 | Full month
Apr’26 | 1782.1 | 156 | 115 | 7.7483 | 2 | Full month
May’26 | 1785 | 156 | 115 | 7.7609 | 2 | Full month
Jun’26 | 868 | 156 | 115 | 7.5478 | 1 | Partial month (divisor=1)

## Productivity Insights
Productivity Analysis — Q1, Q2 & Q3-to-Date
Q1 and Q2 are complete (six sprints each). Q3TD covers SP13–15 and 26 of 29 applications; only Q1→Q2 is a completed-quarter comparison.
Q1 portfolio | Q2 portfolio | Q1→Q2 | Q3TD portfolio | Q2→Q3TD* | Q3TD coverage | Complete histories | Story in brief
7.2464 | 7.6899 | 6.121% | 7.8106 | 1.569% | 26 of 29 | 25 of 29 | Portfolio productivity rose from 7.2 in Q1 to 7.7 in Q2, a confirmed 6.1% increase. Q3TD is 7.8, only 1.6% above Q2 and based on three sprints, so it indicates stability with slight upside rather than a completed-quarter improvement. Among 25 applications with complete history, nine show sustained increases, while five show sustained declines. Seven improved in Q2 but have reversed direction in Q3TD, making them the main monitoring group.
Portfolio three-period trend | [5 empty] | Application trend patterns
Period | Coverage | Portfolio productivity | Change vs prior | Interpretation |  | Pattern | Count | Applications
Q1 | SP1–6 (complete) | 7.2464 |  | Baseline complete quarter |  | Sustained increase | 9 | XM Velocity 1/Xceeders, Xumo, BXT, DevOps, NWT-FSM, Platform, Celestial (Titan), Celestial (Universal), Flow Engine (prometheus)
Q2 | SP7–12 (complete) | 7.6899 | 6.121% | Confirmed quarter-over-quarter change |  | Sustained decline | 5 | Account Services - XM PDF, XM360 CBM/Phoenix, XM360 Supersonix, NWT - PSNB, XRM - VOIXM Scrum
Q3TD* | SP13–15 (partial) | 7.8106 | 1.569% | Preliminary direction only |  | Q3TD recovery | 3 | Field Experience, Flow Engine (optimus), XRM - Video Scrum
[6 empty] | Q3TD reversal | 7 | Account Services, Account Services - BRE, Assisted Tools, CPOS, NWT - UI, XRM, XRM - HSD Scrum
[6 empty] | Stable / mixed | 1 | Right Answers
Confirmed Q1 → Q2 movers | [5 empty] | Provisional Q2 → Q3TD signals
Application | Q1 | Q2 | Δ | Assessment |  | Application | Q2 | Q3TD* | Δ* | Assessment
Right Answers | 4.2494 | 10 | 5.7506 | Largest increase |  | BXT | 6.7956 | 9.17 | 2.3744 | Largest positive signal
NWT-FSM | 5.1245 | 8.0883 | 2.9638 | Second-largest increase |  | DevOps | 6.7956 | 9.17 | 2.3744 | Largest positive signal
Account Services - NOW | 7.5 | 10 | 2.5 | Third-largest increase |  | Celestial (Titan) | 13.0333 | 14.0667 | 1.0333 | Third positive signal
NWT - Core | 8.06 | 4.2967 | -3.7633 | Largest decline |  | Account Services - BRE | 13.6667 | 11.5 | -2.1667 | Largest negative signal
XM360 CBM/Phoenix | 7.4375 | 5.8142 | -1.6233 | Second-largest decline |  | XM360 Supersonix | 7.48 | 5.3767 | -2.1033 | Second negative signal
Account Services - XM PDF | 11.7361 | 10.175 | -1.5611 | Third-largest decline |  | CPOS | 6.425 | 5.0833 | -1.3417 | Third negative signal
Analyst conclusion
The reliable conclusion is that productivity improved in Q2 versus Q1. Q3TD currently holds that gain at portfolio level, but the application mix is uneven: sustained gains coexist with seven early reversals and five sustained declines. Prioritize the sustained-decline and Q3TD-reversal groups, while validating whether BXT, DevOps, and other positive Q3TD signals persist as more sprints are completed.
Note on I9: Rebuilt as a legacy CSE array formula (TEXTJOIN+IF) in place of the original dynamic-array TEXTJOIN+FILTER, which this recalculation engine cannot evaluate (pre-existing #NAME? in the source file). Produces the same comma-separated application list.

## Lead Observations
Application Productivity — Q1, Q2 & Q3-to-Date
Q1 and Q2 are complete six-sprint periods. Q3TD contains SP13–15 only; Q3TD patterns are preliminary and must be revisited as further sprints are added.
Q1 portfolio | Q2 portfolio | Q1→Q2 | Q3TD portfolio | Q2→Q3TD* | Q3TD coverage | Complete 3-period history
7.2464 | 7.6899 | 6.121% | 7.8106 | 1.569% | 26 of 29 | 25 of 29
Application / Workstream | Three-period pattern | Q1 | Q2 | Q3TD* | Q1→Q2 Δ | Q2→Q3TD Δ* | Three-period observation | Question for application lead | Notes from lead
Account Services | Q3TD reversal | 10.3009 | 11.2806 | 10.3833 | 0.97963 | -0.89722 | Q1 10.3 → Q2 11.3 → Q3TD 10.4. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
Account Services - BRE | Q3TD reversal | 11.6667 | 13.6667 | 11.5 | 2 | -2.1667 | Q1 11.7 → Q2 13.7 → Q3TD 11.5. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
Account Services - NOW | Data gap | 7.5 | 10 |  | 2.5 |  | Q3TD is missing; Q1 was 7.5 and Q2 was 10.0. | When will Q3TD data be available, and should the missing value be treated as pending rather than zero?
Account Services - XM PDF | Sustained decline | 11.7361 | 10.175 | 9.2667 | -1.5611 | -0.90833 | Q1 11.7 → Q2 10.2 → Q3TD 9.3. Pattern: sustained decline; Q3TD remains partial. | What persistent constraint has reduced productivity since Q1, and what corrective action is planned?
Assisted Tools | Q3TD reversal | 7.2401 | 7.3777 | 7.041 | 0.13763 | -0.33674 | Q1 7.2 → Q2 7.4 → Q3TD 7.0. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
CPOS | Q3TD reversal | 6.2083 | 6.425 | 5.0833 | 0.21667 | -1.3417 | Q1 6.2 → Q2 6.4 → Q3TD 5.1. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
XM Velocity 1/Xceeders | Sustained increase | 7.0168 | 7.2721 | 7.85 | 0.25526 | 0.57795 | Q1 7.0 → Q2 7.3 → Q3TD 7.9. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
XM Velocity 2/Xplorers | Data gap | 6.1706 | 6.6086 |  | 0.43801 |  | Q3TD is missing; Q1 was 6.2 and Q2 was 6.6. | When will Q3TD data be available, and should the missing value be treated as pending rather than zero?
XM360 CBM/Phoenix | Sustained decline | 7.4375 | 5.8142 | 5.295 | -1.6233 | -0.51917 | Q1 7.4 → Q2 5.8 → Q3TD 5.3. Pattern: sustained decline; Q3TD remains partial. | What persistent constraint has reduced productivity since Q1, and what corrective action is planned?
XM360 Supersonix | Sustained decline | 7.6258 | 7.48 | 5.3767 | -0.14583 | -2.1033 | Q1 7.6 → Q2 7.5 → Q3TD 5.4. Pattern: sustained decline; Q3TD remains partial. | What persistent constraint has reduced productivity since Q1, and what corrective action is planned?
Xumo | Sustained increase | 8.9817 | 10.6667 | 11.6 | 1.685 | 0.93333 | Q1 9.0 → Q2 10.7 → Q3TD 11.6. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
BXT | Sustained increase | 6.285 | 6.7956 | 9.17 | 0.51056 | 2.3744 | Q1 6.3 → Q2 6.8 → Q3TD 9.2. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
DevOps | Sustained increase | 6.285 | 6.7956 | 9.17 | 0.51056 | 2.3744 | Q1 6.3 → Q2 6.8 → Q3TD 9.2. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
Field Experience | Q3TD recovery | 7.0857 | 6.5309 | 7.4108 | -0.55483 | 0.87994 | Q1 7.1 → Q2 6.5 → Q3TD 7.4. Pattern: q3td recovery; Q3TD remains partial. | What changed after the Q2 decline, and is the Q3TD recovery supported by enough sprint evidence?
NWT - Core | Data gap | 8.06 | 4.2967 |  | -3.7633 |  | Q3TD is missing; Q1 was 8.1 and Q2 was 4.3. | When will Q3TD data be available, and should the missing value be treated as pending rather than zero?
NWT - PSNB | Sustained decline | 7.3917 | 5.875 | 5.5 | -1.5167 | -0.375 | Q1 7.4 → Q2 5.9 → Q3TD 5.5. Pattern: sustained decline; Q3TD remains partial. | What persistent constraint has reduced productivity since Q1, and what corrective action is planned?
NWT - UI | Q3TD reversal | 7.7667 | 8.4222 | 8.11 | 0.65556 | -0.31222 | Q1 7.8 → Q2 8.4 → Q3TD 8.1. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
NWT-FSM | Sustained increase | 5.1245 | 8.0883 | 9.0333 | 2.9638 | 0.945 | Q1 5.1 → Q2 8.1 → Q3TD 9.0. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
NWT-FSM 2 (NOVA) | No Q1 baseline |  | 5.9722 | 7 |  | 1.0278 | No Q1 baseline. Q2 was 6.0 and Q3TD is 7.0; the Q3TD comparison remains preliminary. | Why is Q1 unavailable, and what baseline should be used to assess this application?
Platform | Sustained increase | 6.6549 | 8.2755 | 8.8333 | 1.6206 | 0.55779 | Q1 6.7 → Q2 8.3 → Q3TD 8.8. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
Celestial (Titan) | Sustained increase | 11.8286 | 13.0333 | 14.0667 | 1.2048 | 1.0333 | Q1 11.8 → Q2 13.0 → Q3TD 14.1. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
Celestial (Universal) | Sustained increase | 8.8733 | 9.4514 | 10.191 | 0.5781 | 0.73952 | Q1 8.9 → Q2 9.5 → Q3TD 10.2. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
Flow Engine (optimus) | Q3TD recovery | 4.4167 | 4.2917 | 4.5 | -0.125 | 0.20833 | Q1 4.4 → Q2 4.3 → Q3TD 4.5. Pattern: q3td recovery; Q3TD remains partial. | What changed after the Q2 decline, and is the Q3TD recovery supported by enough sprint evidence?
Flow Engine (prometheus) | Sustained increase | 3.9067 | 4.6011 | 5.4089 | 0.69444 | 0.80778 | Q1 3.9 → Q2 4.6 → Q3TD 5.4. Pattern: sustained increase; Q3TD remains partial. | Which repeatable practices drove improvement from Q1 through Q3TD, and can they be sustained through quarter-end?
Right Answers | Stable / mixed | 4.2494 | 10 | 10 | 5.7506 | 0 | Q1 4.2 → Q2 10.0 → Q3TD 10.0. Pattern: stable / mixed; Q3TD remains partial. | What explains the stable or mixed pattern, and what should be monitored in the remaining Q3 sprints?
XRM | Q3TD reversal | 5.7249 | 5.9776 | 5.7534 | 0.25274 | -0.22419 | Q1 5.7 → Q2 6.0 → Q3TD 5.8. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
XRM - HSD Scrum | Q3TD reversal | 4.8906 | 5.6742 | 4.6333 | 0.78369 | -1.0409 | Q1 4.9 → Q2 5.7 → Q3TD 4.6. Pattern: q3td reversal; Q3TD remains partial. | What changed after the Q2 improvement, and is the Q3TD reversal caused by capacity, complexity, dependencies, scope, or timing?
XRM - Video Scrum | Q3TD recovery | 6.4148 | 6.392 | 7.0603 | -0.022879 | 0.66833 | Q1 6.4 → Q2 6.4 → Q3TD 7.1. Pattern: q3td recovery; Q3TD remains partial. | What changed after the Q2 decline, and is the Q3TD recovery supported by enough sprint evidence?
XRM - VOIXM Scrum | Sustained decline | 5.8692 | 5.8667 | 5.5667 | -0.0025758 | -0.3 | Q1 5.9 → Q2 5.9 → Q3TD 5.6. Pattern: sustained decline; Q3TD remains partial. | What persistent constraint has reduced productivity since Q1, and what corrective action is planned?